## Light
PROJECT: Smart Triage with AI
Tel Aviv University | [6 empty] | Legend: |  | Planning & Preparation | [9 empty] | Development & Implementation | [12 empty] | Documentation | [6 empty] | Evaluation & Visual Interface | [11 empty] | Progress Monitoring & Mentorship | [12 empty] | Bureaucracy & Procurement
Lior & Liniv
Project start date: | 2025-10-26
[6 empty] | October | [5 empty] | November | [29 empty] | December | [30 empty] | January | [30 empty] | February | [27 empty] | March | [30 empty] | April | [29 empty] | May | [30 empty] | June | [29 empty] | July
[6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17 | [6 empty] | Week 18 | [6 empty] | Week 19 | [6 empty] | Week 20 | [6 empty] | Week 21 | [6 empty] | Week 22 | [6 empty] | Week 23 | [6 empty] | Week 24 | [6 empty] | Week 25 | [6 empty] | Week 26 | [6 empty] | Week 27 | [6 empty] | Week 28 | [6 empty] | Week 29 | [6 empty] | Week 30 | [6 empty] | Week 31 | [6 empty] | Week 32 | [6 empty] | Week 33 | [6 empty] | Week 34 | [6 empty] | Week 35 | [6 empty] | Week 36 | [6 empty] | Week 37 | [6 empty] | Week 38 | [6 empty] | Week 39 | [6 empty] | Week 40
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2025-10-26 to 2026-08-01
Preparing a Gantt | Development & Implementation | Lior | 100% | 2025-10-26 | 1
Specification document | Planning & Preparation | Lior | 100% | 2025-10-26 | 1
Signing an NDA | Planning & Preparation | Lior & Liniv | 100% | 2025-10-26 | 1
Receiving a data file | Bureaucracy & Procurement | Lior | 100% | 2025-10-26 | 1
Connecting Gemini API Infrastructure | Development & Implementation | Lior | 100% | 2025-10-26 | 1
Connecting Vertex AI GCP Infrastructure | Development & Implementation | Lior | 50% | 2025-10-26 | 30
Developing the first 6 agents | Development & Implementation | Lior | 100% | 2025-10-26 | 2
Agents' run on a single case | Development & Implementation | Lior | 100% | 2025-10-26 | 1
Obtaining a license for OpenAI | Bureaucracy & Procurement | Lior | 50% | 2025-10-26 | 30
Lecture 1 | Evaluation & Visual Interface | Lior & Liniv | 100% | 2025-10-27 | 1
Literature review on similar products | Documentation | Liniv | 70% | 2025-10-27 | 20
Q&A session with Dr. Mor | Progress Monitoring & Mentorship | Lior & Liniv | 100% | 2025-11-09 | 1
Development of two additional agents | Development & Implementation | Lior | 0% | 2025-11-10 | 5
Writing Presentation for Dr.Mor | Documentation | Lior & Liniv | 0% | 2025-11-10 | 19
Presentation for Dr.Mor Submission | Progress Monitoring & Mentorship | Lior | 0% | 2025-11-30 | 1
Writing first Report | Documentation | Lior & Liniv | 0% | 2025-11-11 | 20
Gantt Presentation | Evaluation & Visual Interface | Lior & Liniv | 0% | 2025-11-13 | 6
Lecture 2 | Evaluation & Visual Interface | Lior & Liniv | 0% | 2025-11-24 | 1
Creating agents using the Open AI API | Development & Implementation | Lior | 0% | 2025-11-25 | 14
Comparing Open AI and Gemini | Development & Implementation | Lior | 0% | 2025-12-09 | 3
Building a visual interface | Development & Implementation | Lior | 0% | 2025-12-12 | 5
Writing the methods chapter | Documentation | Lior | 0% | 2025-12-12 | 10
First Report | Evaluation & Visual Interface | Lior & Liniv | 0% | 2025-12-29 | 1
Lectrure 3 | Evaluation & Visual Interface | Lior & Liniv | 0% | 2026-03-23 | 1
Preparing a presentation | Documentation | Lior & Liniv | 0% | 2026-03-29 | 10
First Presntation | Evaluation & Visual Interface | Lior & Liniv | 0% | 2026-04-12 | 6
Preparing a poster | Documentation | Lior & Liniv | 0% | 2026-05-18 | 5
Preparing a abstract | Documentation | Lior & Liniv | 0% | 2026-05-20 | 5
Abstract Submission | Evaluation & Visual Interface | Lior & Liniv | 0% | 2026-06-01 | 1
Poster Submission | Evaluation & Visual Interface | Lior & Liniv | 0% | 2026-06-01 | 1
Final Presentation & Poster Presentaion | Evaluation & Visual Interface | Lior & Liniv | 0% | 2026-06-14 | 5
Final Report | Evaluation & Visual Interface | Lior & Liniv | 0% | 2026-07-30 | 1